## Sheet1
Story ID | Story Name | Description | Priority | Iteration (Sprint) number | Acceptance Criteria | Estimation | Notes | Date started (or planned) | Date finished (or planned)
PB-001 | TA - Register Account & Complete CV | As a TA, I need to register an account and complete my resume to apply for TA positions. | High | Sprint 1 | 1. Support email/student ID registration with mandatory field checks; 2. Allow PDF/text resume upload (education/skills/experience); 3. Require email verification post-registration | 5 | Involves three core modules: form validation, PDF CV upload, and email verification. High technical complexity, requiring file storage and verification logic. | 2026-03-15 | 2023-03-23
PB-002 | TA - View Available TA Positions | As a TA, I need to view available TA positions to filter target roles. | High | Sprint 1 | 1. Show course name, TA quota, deadline, skill requirements; 2. Support filtering by course/deadline; 3. Allow clicking to view position details | 3 | Core functions: position list display and filtering. Depends on basic data storage; medium implementation difficulty. | 2026-03-18 | 2026-03-25
PB-003 | MO - Publish TA Position Needs | As a MO, I need to publish TA position needs to recruit qualified TAs. | High | Sprint 1 | 1. Require filling course name, TA count, duties, skills, deadline; 2. Allow preview/editing before publishing; 3. Sync published positions to the list automatically | 5 | Includes position form editing, preview/editing, and publishing synchronization logic. Needs to link with Admin approval process; medium-high complexity. | 2026-03-18 | 2026-03-25
PB-004 | MO - Review TA Applications | As a MO, I need to review TA applications for my course to select candidates. | Medium | Sprint 2 | 1. Display applicant name, resume link, application time; 2. Support filtering by skills/education; 3. Allow "Pass/Fail" marking with comments | 3 | Core functions: applicant list display/filtering and Pass/Fail marking. Depends on application data from PB-006. | 2026-03-25 | 2026-04-02
PB-005 | Admin - Approve MO's Positions | As an Admin, I need to approve MO-published positions to ensure compliance. | Low | Sprint 2 | 1. Highlight pending positions in red; 2. Support "Approve/Reject" (rejection needs reason); 3. Make positions visible to TAs only after approval | 2 | Only requires displaying pending position list and Approve/Reject operations. Simple logic, low complexity. | 2026-03-27 | 2026-04-03
PB-006 | TA - Submit Position Application | As a TA, I need to submit position applications to participate in TA selection. | High | Sprint 1 | 1. Require confirming resume info before submission; 2. Allow adding additional notes; 3. Show "submission success" prompt post-application | 3 | Includes CV confirmation submission, additional notes, and submission prompts. Depends on CV data from PB-001 and position data from PB-002. | 2026-03-20 | 2026-03-27
PB-007 | TA - Check Application Status | As a TA, I need to check my application status to track selection progress. | Medium | Sprint 2 | 1. Show "Pending/Passed/Failed" status for each application; 2. Display MO's feedback if failed; 3. Send notifications for status updates | 2 | Only requires displaying application status and MO feedback. Simple logic, depends on review results from PB-004. | 2026-04-02 | 2026-04-10
PB-008 | MO - Generate TA Offer Letters | As a MO, I need to generate TA offer letters to inform candidates of results. | Medium | Sprint 3 | 1. Support selecting passed TAs to auto-generate offer templates; 2. Allow editing offer content (position info, onboarding time); 3. Support emailing offers | 3 | Includes template generation, offer content filling, and export functions. Needs to link with pass results from PB-004. | 2026-04-15 | 2026-04-21
PB-009 | Admin - View Recruitment Statistics | As an Admin, I need to view recruitment stats to track overall progress. | Low | Sprint 3 | 1. Show application count, hire count, and unfilled positions per course; 2. Support exporting stats reports by time period; 3. Update data in real time | 3 | Includes data statistics, filtering by course/user, and report export. Requires reading full application and position data. | 2026-04-16 | 2026-04-22
PB-010 | All Roles - Reset Account Password | As a user, I need to reset my password to regain access if I forget it. | Medium | Sprint 3 | 1. Support password reset via registered email (verification code); 2. Require new password to meet complexity (8+ chars, letter+number); 3. Force re-login after reset | 2 | Only includes email verification code check, password update, and forced re-login. Serves as the baseline story with the lowest complexity. | 2026-04-18 | 2026-04-25